AGING IN THE COMFORT OF HOME®

# Change-Order Policy

Control process for scope changes, customer requests, hidden conditions, substitutions, and price changes.

| Document Code | VIN-CTRL-08 |
| --- | --- |
| Program | AITCOH Virtual Installer Network™ |
| Version | v1.0 Working Draft |
| Status | Internal control document; legal review required before use |
| Core Principle | Centralized AITCOH customer experience with certified local field execution |

Important: This document is a business-control draft, not legal advice. It should be reviewed by qualified construction, employment, franchise, insurance, licensing, and local-market counsel before execution or publication.

# 1. Purpose

This policy prevents unauthorized field work, pricing disputes, customer confusion, warranty problems, and inconsistent project outcomes. All changes to an approved AITCOH project must be documented and approved in writing before work proceeds, except for emergency stabilization necessary to prevent immediate harm or property damage.

Core Rule No verbal approval, handshake, text-only side agreement, cash agreement, or field promise modifies an AITCOH project. The approved scope changes only through AITCOH’s written change-order process.

# 2. What Counts as a Change Order

| Change Type | Examples |
| --- | --- |
| Added work | Customer asks for additional grab bars, extra railing, another room, extra repair, or new fixture. |
| Scope reduction | Customer wants to remove work, downgrade materials, skip a step, or reduce the finish level. |
| Material substitution | Different product, color, size, fixture, waterproofing system, fastener, ramp component, or finish material. |
| Hidden condition | Rot, mold, water damage, framing issue, electrical/plumbing conflict, substrate failure, code issue. |
| Price change | Any labor, material, travel, permit, disposal, or schedule impact that changes project cost. |
| Schedule impact | Change that extends duration, requires return trip, or affects customer access. |
| Warranty/customer promise change | Any statement that changes AITCOH’s customer obligation or finished-result promise. |

# 3. Change-Order Workflow

Identify the potential change, hidden condition, customer request, or scope conflict.

Pause the affected work area if continuing could create cost, safety, quality, code, or warranty risk.

Document the condition with photos, notes, measurements, and customer request details.

Submit the change-order request to AITCOH through the approved system.

AITCOH reviews scope, pricing, customer impact, schedule, warranty, and compliance implications.

AITCOH communicates approved change order to customer and obtains written customer approval where required.

AITCOH issues written approval to Installer Partner before added or changed work begins.

Installer Partner completes the approved change and uploads required documentation.

# 4. Installer Authority

| Installer May | Installer May Not |
| --- | --- |
| • Identify and document hidden conditions • Explain that AITCOH must approve changes • Send photos and notes to AITCOH • Provide field input on labor/material impact • Stabilize immediate safety hazards | • Quote final price directly to customer unless authorized • Accept cash or side payment • Promise warranty coverage • Change material or scope without written approval • Perform extra work based only on customer verbal approval |

# 5. Emergency Stabilization Exception

If an immediate condition creates a safety risk or risk of active property damage, Installer Partner may take reasonable limited action to stabilize the condition. This exception does not authorize full repair, added scope, final pricing, or expanded project commitments without AITCOH approval.

| Emergency Example | Permitted Limited Action |
| --- | --- |
| Active water leak discovered | Shut off water if safe and permitted; notify AITCOH immediately. |
| Open hazard after demolition | Secure area, cover opening, protect customer access, notify AITCOH. |
| Electrical hazard | Stop work, keep area safe, contact licensed professional/AITCOH as appropriate. |
| Structural concern | Stop affected work, avoid loading or covering condition, notify AITCOH. |

# 6. Change-Order Request Form

| Field | Response |
| --- | --- |
| Project number |  |
| Customer name |  |
| Installer Partner |  |
| Date/time identified |  |
| Change type | Added work / hidden condition / substitution / reduction / schedule / safety / other |
| Description of issue/request |  |
| Photos uploaded? | ☐ Yes ☐ No |
| Measurements/details |  |
| Impact if not approved |  |
| Estimated labor/material impact |  |
| Customer notified that AITCOH approval is required? | ☐ Yes ☐ No |
| AITCOH decision | Approved / Declined / More info needed |
| Customer written approval required? | ☐ Yes ☐ No |
| Final authorization date |  |

# 7. Customer-Facing Language

Approved Language “This is outside the approved scope or may affect the approved work. I need to document it and send it to AITCOH. They will review it and, if appropriate, provide the proper change order before anything changes.”

# 8. Violation Consequences

Unauthorized change work may be excluded from payment.

Installer may be responsible for correction costs, customer credits, or rework caused by unauthorized changes, subject to counsel-reviewed agreement terms.

Repeated violations may result in probation, assignment hold, or network removal.

Side deals, cash agreements, or customer solicitation may result in immediate removal.

# Signature / Acknowledgment

| Party | Name / Title | Signature | Date |
| --- | --- | --- | --- |
| AITCOH Authorized Representative |  |  |  |
| Installer / Contractor |  |  |  |